## task_status
task_id | priority | domain | name | module | status | core_done | e2e_verified | gap | est
P0-gate | P0 | quality | verify_sh | verify.sh | landed | Y | Y | enhance layered | 0.5d
P0-docsync | P0 | quality | doc_code_drift | check-doc-cli-drift.py | landed | Y | Y | zero drift | 0.5d
P0-thirdparty | P0 | quality | third_party_validate | validate_integration.py | landed | Y | Y | 18/18 manifests | 0.5d
P0-merge | P0 | backend | core_dir_merge | core/ | done | Y | Y |  | done
P0-frontend | P0 | frontend | webui_guards_10 | webui/ | done | Y | Y |  | done
P0-i18n | P0 | frontend | i18n_6_lang | webui/src/i18n/ | done | Y | Y |  | done
P0-security | P0 | backend | M1_security_6 | rbac+audit_store+credentials | done | Y | partial: no real auth | RBAC dispatch not wired | done
P0-kv | P0 | backend | M2_kv_cache | cache/ | done | Y | partial: runtime | real provider not wired | done
P0-bench | P0 | backend | Bench-30 | bench/ | done | Y | partial: no real run | baseline/optimized 3x not done | done
P0-onboard | P0 | frontend | OnboardingOverlay | webui/ | done | Y | Y |  | done
P0-connstate | P0 | frontend | GatewayReadiness | webui/ | done | Y | Y |  | done
P0-cache-honesty | P0 | backend | cache_honesty_3tier | cache/ | done | Y | Y |  | done
P0-bloom-redline | P0 | backend | Bloom_redline_guard | bloom.yaml | done | Y | Y |  | done
P0-invariants | P0 | arch | INV1-9_frozen | AGENTS.md | done | Y | Y |  | done
P0-msi | P0 | desktop | Tauri_MSI | gui/src-tauri/ | done | Y | partial: 3 defects | API Key 401 / conn state / zero status | done
P0-navgroup | P0 | frontend | sidebar_nav_grouping | webui/src/router/ | done | Y | Y |  | done
P0-controlcenter | P0 | frontend | Control_Center | webui/src/views/ | done | Y | Y |  | done
P0-clicontract | P0 | backend | CLI_output_contract | cli/ | done | Y | Y |  | done
P0-byok | P0 | backend | credential_encrypt_BYOK | credentials/ | done | Y | partial: M5 pending | vault first-start UI/CLI | done
P0-zerostate | P0 | frontend | zero_status_bar | webui/ | done | Y | Y |  | done
M1.6 | P0 | frontend | UI_permission_boundary | webui/SettingsView | not_done | - | - | settings page disclaimer text | 0.5d
M3.5 | P0 | backend | object_version+audit_query | - | not_done | - | - | version snapshot+diff+rollback+audit | 3d
M3.6 | P0 | frontend | ops_webui_panel | webui/ | not_done | - | - | OpsPanel 4 panels Vue3+Lucide | 3-5d
M4.3 | P1 | backend | cn_model_tuning | - | not_done | - | - | intent routing/budget/template per token | 3d
M4.4 | P1 | backend | multimodal_direct | - | not_done | - | - | image part to vision model to WebUI | 3d
M4.6 | P1 | backend | windows_control | computer_use.rs | not_done | - | - | UiaDriver/InputDriver impl | 3d
M5.1 | P0 | desktop | doctor_checkup | core/src/doctor/ | not_done | Y: 11tests | partial: Fresh-Machine | 7 items+JSON+vision | 1d
M5.2 | P0 | desktop | python_probe_chain | pyengine/sidecar.rs | not_done | - | - | env to python/python3/py-3+guide | 1d
M5.3 | P0 | desktop | resource_integrity_gate | build.rs | not_done | - | - | skills>=40M/webui freshness | 0.5d
M5.4 | P0 | desktop | Fresh-Machine_Gate | - | not_done | - | - | S1/S2/S3 green | 2d
M5.5 | P0 | desktop | release_archive | dist/ | not_done | - | - | MSI+NSIS+zip same version+SHA256 | 0.5d
P1-agentweb | P1 | frontend | agentweb_21_fixes | marguerite-agent-web/ | pending | - | - | 21 review improvements | 5d
P1-redesign | P1 | frontend | desktop_visual_redesign | gui/ | pending | - | - | oriental botanical warm style | 10d
P1-decost | P1 | backend | M2_optimized_variant | - | pending | - | - | cost optimization variants | 5d
P1-dag | P1 | backend | agent_runtime_dag | - | pending | - | - | DAG concurrent execution | 5d
P1-mcp | P1 | backend | mcp_tool_extend | - | pending | - | - | MCP tool extension | 3d
P1-browser | P1 | frontend | browser_cockpit | - | pending | - | - | browser cockpit enhance | 3d
P1-memdistill | P1 | backend | memory_auto_distill | - | pending | - | - | 3-tier memory distill | 3d
P1-settings | P1 | frontend | settings_refactor | - | pending | - | - | settings panel refactor | 3d
P1-plugin | P1 | backend | PluginManifest_extend | - | pending | - | - | PluginManifest extension | 2d
P1-errorbound | P1 | frontend | error_boundary | - | pending | - | - | error boundary+fallback | 2d
P1-msgretry | P1 | frontend | message_retry_idempotent | - | pending | - | - | message retry+idempotent | 2d
P1-swarm | P1 | backend | orchestrator_swarm | - | pending | - | - | swarm optimization | 3d
P1-editor | P1 | frontend | workspace_editor | - | pending | - | - | editor enhance | 3d
P1-session | P1 | backend | session_persist | - | pending | - | - | session persistence | 3d
P1-audit | P1 | backend | audit_log_enhance | - | pending | - | - | audit log enhance | 2d
P1-routing | P1 | backend | model_routing_smart | - | pending | - | - | smart routing | 3d
P1-routeguard | P1 | backend | route_guard | - | pending | - | - | route guard polish | 2d
P1-ratelimit | P1 | backend | rate_limit_upgrade | - | pending | - | - | rate limit upgrade | 2d
P1-hotkey | P1 | frontend | hotkey_system | - | pending | - | - | hotkey system | 3d

## status_summary
status | count | pct | note
done | 17 | 25.4% | P0 core all done and verified
landed_pending | 3 | 4.5% | P0 gate scripts landed, need CI solidify
partial_core_done | 18 | 26.9% | core/engine/contract/tests pass, e2e gap
not_done | 6 | 9.0% | M1.6/M3.5/M3.6/M4.3/M4.4/M4.6
pending_P1 | 19 | 28.4% | next phase focus
pending_P2 | 18 | 26.9% | mid-term
pending_P3 | 10 | 14.9% | long-term exploration
M5_not_done | 5 | 7.5% | packaging and delivery
memory_not_done | 3 | 4.5% | desktop onboarding/visual redesign/MSI defects

## action_plan
priority | task_id | name | gap | plan | est | deps
P1-immediate | M1.6 | UI permission boundary | no disclaimer in settings | SettingsView add text + 6 lang i18n | 0.5d | none
P1-immediate | MSI-P0 | API Key 401 fatal | no pre-check before send | chat send pre-check + guide popup | 0.5d | none
P1-immediate | MSI-P1a | conn state UI contradiction | Readiness shows connected but not | unify GatewayReadiness logic | 0.5d | none
P1-immediate | MSI-P1b | status bar zero pollution | zero values + stale dist | zero filter + dist cleanup | 0.5d | none
P1-immediate | ONBOARD | desktop onboarding design | report not produced | produce design doc + reuse overlay | 1d | none
P2-near | M3.6 | OpsPanel webui | 4 panels not done | register OpsPanel + Vue3 + Lucide + ops.* | 3-5d | M3.1-M3.4
P2-near | M5.1 | doctor checkup | 7 items not verified | execute PACKAGING 6.1 + vision | 1d | none
P2-near | M5.2 | python probe chain | not implemented | env to python3 + guide AC-19 | 1d | none
P2-near | M5.3 | resource integrity gate | not implemented | skills>=40M/webui freshness | 0.5d | none
P2-near | M5.4 | Fresh-Machine Gate | 3 scenarios not verified | S1/S2/S3 green AC-19-27 | 2d | M5.1-M5.3
P2-near | M5.5 | release archive | not done | MSI+NSIS+zip same version+SHA256 | 0.5d | M5.4
P3-mid | P1-AgentWeb | agent-web 21 fixes | 21 improvements not done | fix per review checklist | 5d | none
P3-mid | P1-redesign | desktop visual redesign | oriental botanical not started | design doc + full CSS/component rewrite | 10d | none
P4-strategic | STR-05 | R6 first-run | onboarding not implemented | install guide + provider config + 5s | 3d | M5.4
P4-strategic | STR-07 | D2/D3/R1 metrics | no real Bench-30 Omni report | unified baseline + 3x median | 5d | M2.6

## doc_completeness
path | type | size | status | code_consistency | note
AGENTS.md | root core | 174 lines | authoritative | 19 routes match, 2425 baseline | repo guide
README.md | root core | 130 lines | authoritative | 4-frontend arch accurate | unified entry
LOCAL_MODEL_WORKBENCH.md | root core | 333 lines | complete | RPC 14 methods match | local model workbench
PHASE_C_PROGRESS.md | root core | 49 lines | complete | C1-C4 all done | notify/hotkey/tray/menu
PHASE_D_PROGRESS.md | root core | 66 lines | complete | run_turn + React events | GUI frontend
CHANGELOG.md | root core | 485 lines | active | v0.1.5 to v32 complete | version history
opsdev/SPEC.md | plan doc | 313 lines | locked | F1-F26 partial | functional spec
opsdev/IMPL-PLAN.md | plan doc | 171 lines | active | M0-M5 partial | implementation plan
opsdev/UNFINISHED-TASKS.md | plan doc | 162 lines | active | updated to 08-31 | task ledger
opsdev/STRATEGY-ALIGNMENT.md | plan doc | 127 lines | locked | 47d roadmap confirmed | strategy align
opsdev/PACKAGING.md | plan doc | 239 lines | standard | std landed, verify pending | packaging std
opsdev/FINAL-DESIGN.md | plan doc | 225 lines | authoritative | modules accurate | final design
.trae/cli-workbench/ | spec doc | 7 md | complete | Phase B TUI done | CLI workbench spec
.trae/harden-optimize/ | spec doc | 3 md | complete | all tasks [x] done | harden spec
.trae/opensquilla-fusion/ | spec doc | 2 md | complete | fusion design done | fusion spec
.workbuddy/memory/ | log doc | 20+ md | active | 08-04 to 09-01 | work logs
docs/UNIFIED_WORKBENCH_DESIGN.md | artifact | 435 lines | done | arch + UI/UX | unified workbench
docs/dev-task-list-v1.0.xlsx | artifact | 18KB | done | 67 tasks | dev task list
docs/quality-audit-v3.0.xlsx | artifact | - | done | 31 issues cleared | quality audit
docs/acceptance-v1.0.md | artifact | - | done | 64 items all pass | acceptance report